## Goals
This project is a part of online course
Project Name: | SeleniumJunitCyclos_DataDriven
ApplicationUnderTest: | https://demo.cyclos.org/#login | Cyclos.org is an Open source online banking application. This site has three user interface as demo user, demoUSer2, demoUser3
Author: | Bharathi Ramapatnam
Tools: | SeleniumWebdriver - 2.44 Eclipse -
Date:
1 | Implement simple and reusable Framework | Complete
2 | one set of Test Cases to run in Chrome, Firefox and I.e. | Complete
3 | Run mode of the tests are controlled through Excel. | Complete
4 | Automate few test cases through Seleniumebdriver | Complete
5 | Parameterise tests though excel | Complete
6 | Generate/Email Reports | Incomplete
7 | Compile tests to run through Ant/cmd | Complete

## Plan
Status | Plan | Notes
Done | Create New Java Project in Eclipse
Done | Introduce Required project jar files as reference Libraries
Done | Create com.cyclos.util Package
Done | create com.cyclos.dataTable Package
Done | Create com.cyclcos.tests package
Done | Create com.cyclos.config package
Done | Create com.cyclos.Reports package
Done | Create com.cyclos.Rough : for rough work
Done | Create or.properties file in Config package
Done | Create config.properties file in config package
Done | Create class TestBase class in util Package
Done | Load properties file in TestBase class
Done | Initialise Webdriver class @Before Annotation.
Done | Create xlsx file called suite1 and include in datatable Package
Done | Incude test cases in suite1
Done | create class Testutil under util package
Done | Create reusable Functions:
Done | isTestCaseRunnable
Done | takeScreenshot
Done | dologin
Done | logout
Done | getdata
Done | isElementPresent
Done | introduce webdriver implicit waits/pageload
Done | Introduce log4j properties file in config package
Done | create some testcases under package tests: introduce @Test annotation | Register to Cyclos as NewUser
Done |  | Register to Cyclos as NewUser
Done |  | Register to Cyclos as Existing user and validate the error message
Done |  | Login to Cyclos
Done |  | Validate Facebook,youTube,Linkedin links on the landing page: TakescreenShots Validate Change password link on the landing page
Banking: Transfer funds from user1 to user2
Introduce try catch block for error reporting
Batch run testcases : Create a class FirstSuiteRunner
Introduce @Runwith annotation
@SuiteClasses
| Parameterise the login test with different data @RunWith(Parameterized.class) | Login Parameter test : login to cyclos as demo,demo2,demo3 user and Take screenshots
| Parameterise the Search user test | search for existing user with different data: validate the result